Overview and resourcing strategy

This application requests the minimum set of resources required to deliver four tightly scoped objectives over 12 months. The budget prioritises specialist staff time and access to institutional infrastructure to enable full-season analysis of professional football match data using Topological Data Analysis (TDA). The Full Economic Cost is £95,233, with the EPSRC contribution at 80%. Costs are concentrated where they deliver the highest value: a six-month Research Associate (RA) appointment to execute concurrent, large-scale data processing and methods implementation; Principal Investigator (PI) time for scientific leadership, early pipeline validation, and end-to-end coordination; targeted Co-Investigator (Co-I) input for domain expertise and methodological rigour; and access to institutional high-performance computing (HPC), secure storage, and meeting spaces. No new equipment purchases are required; the project leverages mature open-source libraries and existing institutional facilities, ensuring excellent value for money and timely delivery.

Project staff

Research Associate (6 months, 100% FTE).
The RA is essential to achieving all four objectives within the 12-month timeframe. Their primary responsibility is to set up and operate a concurrent processing pipeline and to complete the full-season analysis across the Championship dataset. This entails: (i) implementing persistent homology computations at multiple scales per frame, (ii) undertaking pattern formation method development with temporal tracking and baseline signature identification across at least three tactical systems, (iii) delivering the temporal evolution module using persistence landscapes, and (iv) performing statistical validation, quality control, and comprehensive code documentation.

This allocation is justified on both technical and operational grounds. Preliminary work has established sub-second to two-second per-frame performance on the institutional HPC cluster, making concurrent processing of hundreds of matches tractable. Concentrating specialist effort over months 4–9 allows the RA to (a) complete pipeline setup and optimisation early in their appointment and (b) drive systematic analysis of the remaining matches at scale, while ensuring quality assurance and reproducibility. The RA’s skill set—Python, parallelisation, TDA libraries (ripser, GUDHI, giotto-tda), and statistical analysis—aligns directly with the project’s computational demands and avoids the need for external contractors or additional licences. The appointment length is calibrated to deliver the full season analysis while preserving resource for PI-led integration, write-up, and dissemination in months 10–12.

Principal Investigator (165 hours).
The PI provides scientific direction, methodological leadership, and coordination that cannot be delegated. The PI will: (i) develop and validate the initial pipeline and analyse 15–20 games in months 1–3 to establish a robust foundation; (ii) supervise and mentor the RA during months 4–9, ensuring methodological fidelity and quality standards; (iii) manage the partnership critical for data access (Swansea City AFC–StatsBomb); (iv) coordinate the end-to-end full-season synthesis integrating all 540 matches in months 10–12; and (v) lead event correlation, manuscript preparation, and the subsequent Standard Grant planning. The requested hours (averaging ~3.2 hours/week) represent an optimal balance between strategic oversight, hands-on methodological development, and the PI’s other commitments, ensuring continuity and timely delivery without over-resourcing.

Co-Investigators (66 hours total).
Two Co-Is provide targeted, high-value expertise without duplication of the PI’s role.

- Sports science (33 hours): Interprets topological outputs in the context of professional football tactics, supports validation, and translates findings into practically meaningful insights for performance analysis.

- Applied mathematics (33 hours): Ensures theoretical rigour in TDA methodology, supports statistical validation, and contributes to framework refinement suitable for top-tier publications.

This measured input guarantees comprehensive coverage across computational topology, sports science, and applied mathematics, strengthening the research’s validity and impact while maintaining cost-effectiveness.

Facilities and infrastructure

High-performance computing, secure storage, estates, and technical support are justified as they enable reliable, compliant, and efficient delivery at scale. The project relies on the institutional HPC cluster to execute concurrent pipelines and compute persistent homology across large volumes of match-frame data. Access to secure, GDPR-compliant storage is required to hold raw, intermediate, and processed datasets as well as reproducibility artefacts (code, logs, validation reports). Estates costs provide office and meeting space across the participating departments, facilitating collaboration, supervision, and industry engagement. Modest technician time covers HPC account provisioning, environment setup, data management integration, and support for open-source library dependencies. Crucially, there is no need for new equipment purchases or commercial software licences: the project exploits mature, well-supported open-source TDA libraries, further improving value for money and sustainability.

Optimal use of resources and delivery plan

The resource profile has been carefully phased to maximise productivity and minimise waste:

- Months 1–3: PI develops and validates the pipeline, analyses 15–20 games, and finalises the RA work plan and quality criteria. This early validation de-risks the subsequent scale-up and ensures the RA can begin with a tested framework.

- Months 4–9: RA establishes concurrent processing and completes the full-season analysis across the remaining matches, implements pattern formation and temporal evolution methods, and documents the codebase to reproducible standards. PI supervises, ensuring methodological coherence and timely milestones; Co-Is provide targeted inputs at key decision points (e.g., model assumptions, validation thresholds, interpretation of outputs).

- Months 10–12: PI integrates outputs across all 540 matches, conducts event correlation analyses, finalises figures and tables, and leads manuscript preparation and Standard Grant development.

This plan optimises specialist expertise at the right time, mitigates risks through early validation, and concentrates computationally intensive activity within the RA appointment. It also ensures that dissemination and future funding preparation are resourced appropriately.

Outcomes, impact, and value for money

The requested resources directly support high-impact, reproducible outputs: a validated analytical framework, open and well-documented code, and rigorous multi-match results interpretable by sports scientists and analysts. Leveraging institutional HPC and secure storage eliminates the need for capital expenditure and reduces recurring overheads. Relying on mature open-source libraries removes licensing costs and aligns with EPSRC’s principles on reproducibility and sustainability.

Partnership value is considerable: in-kind full-season data access and domain insight from Swansea City AFC enable a real-world, high-quality dataset without direct cost to EPSRC. This amplifies impact by ensuring that methods and findings are grounded in professional practice, with clear pathways to adoption in performance analysis and coaching contexts. The RA’s involvement in publication and code stewardship supports career development, contributing to the skills pipeline in data-driven sports data-science and computational topology. Collectively, these resources maximise the probability of producing publishable, citable outputs and provide a strong platform for a subsequent Standard Grant.

Risk management and assurance

The phased approach, early pipeline validation by the PI, followed by RA-led scale-up, reduces technical risk and ensures continuity. Institutional facilities guarantee compliance (e.g., data protection) and reliability (e.g., storage redundancy, supported HPC environments). Code documentation, statistical validation, and quality control are embedded throughout, ensuring that results are robust, reproducible, and audit-ready. The modest technician input further mitigates operational risks by providing support where needed without inflating costs.