## RESOURCES AND COSTS

Total Full Economic Cost (fEC): £95,233
EPSRC Contribution (80%): £76,186
Institutional Contribution (20%): £19,047

### Cost Breakdown

#### Directly Incurred Costs

Staff – DI Staff: £24,670

- Research Associate (100% FTE, 6 months, Months 4–9, Grade 7, Spine Point 30): £24,670

  - Sets up concurrent processing pipeline and analyses all remaining games from the full Championship season (~520–525 games from total 540, ~77,000–78,000 frame analyses), pattern formation methods, temporal evolution implementation, code documentation

  - Skills: Python, TDA libraries (ripser, GUDHI, giotto-tda), parallel processing, statistical analysis

Total Directly Incurred Costs: £24,670

#### Directly Allocated Costs

Staff – DA Investigators: £13,914

- Principal Investigator (Dr Rowan Brown, Biomedical Engineering, 165 hours): £8,106

  - Pipeline development and analysis of 15–20 initial games (Months 1–3) before RA arrival, project direction, RA supervision (Months 4–9), industry partnerships, full-season analysis coordination incorporating all 540 games (Months 10–12), manuscript preparation, Standard Grant preparation

- Co-Investigator (Professor Liam Kilduff, Sport and Exercise Sciences, 33 hours): £2,904

  - Sports science expertise, tactical pattern interpretation, validation support

- Co-Investigator (Professor Gibin Powathil, Mathematics, 33 hours): £2,904

  - Applied mathematics expertise, TDA methodological guidance, statistical validation

Estates: £17,828

- Laboratory and office space across three departments, HPC computational facilities access, secure data storage, meeting spaces

Infrastructure Technicians: £593

- Technical support for local HPC cluster access, data management, software integration

Total Directly Allocated Costs: £32,334

#### Indirect Costs

Indirect Costs: £38,228

- Institutional overhead: administration, facilities management, support services, compliance and governance

Total Indirect Costs: £38,228

Project Total: £95,233

Note: Open access publication costs are covered by UKRI block grants to research organisations, in accordance with EPSRC policy.

## Justification of Resources

This section justifies the more costly resources and demonstrates how resources are comprehensive, appropriate, justified, and represent optimal use to achieve intended outcomes and maximise potential impacts.

### Project Staff

Research Associate (6 months, 100% FTE, Months 4–9, £24,670)
Essential for achieving all four project objectives within the 12-month timeframe. The 6-month appointment (Months 4–9) concentrates specialist computational effort for setting up concurrent pipeline and analysing all remaining games from the full Championship season:

- Objective 1 (Months 4–9): RA sets up concurrent processing pipeline and analyses all remaining games from the 540-match season (~520–525 games, ~77,000–78,000 frame analyses). Processing with persistent homology computation at three scales per frame, statistical validation, and quality control. Pipeline architecture enables simultaneous analysis of multiple games, maximising computational efficiency. PI coordinates final analysis incorporating all 540 games (Months 10–12).

- Objective 2 (Months 4–9): Pattern formation method development requiring algorithmic implementation, temporal tracking, and baseline signature identification for ≥3 tactical systems, applied across remaining games during RA period

- Objective 3 (Month 7): Temporal evolution method implementation using persistence landscapes, applied during analysis of remaining games

Optimal Resource Use: Preliminary work demonstrated <2s per-frame computational efficiency using institutional Supercomputing Wales cluster (2-Petaflops), enabling concurrent processing of full season. PI analyses 15–20 initial games (Months 1–3) before RA arrival, establishing validated foundation. RA sets up concurrent processing pipeline (Months 4–5) and executes analysis of all remaining games (Months 6–9). Mature open-source libraries (ripser, GUDHI, giotto-tda) provide robust infrastructure without licensing costs. Phased approach ensures early validation on initial games, intensive specialist effort during RA appointment for analysing remaining games, with PI coordinating full-season analysis completion incorporating all 540 games (Months 10–12), maximising specialist expertise while enabling cost-effective completion.

Maximising Outcomes: Enables achievement of all four research objectives, production of validated reproducible framework, RA career development through co-authorship, code documentation ensuring work continuation, and foundation for Standard Grant application.

Principal Investigator (165 hours, £8,106)
Critical for strategic direction and expertise that cannot be delegated: pipeline development and analysis of 15–20 initial games (Months 1–3) before RA arrival, establishing validated foundation; methodology development; RA supervision and training (Months 4–9) while RA sets up pipeline and analyses remaining games; industry partnership management (crucial for SCAFC–Statsbomb full-season data access); full-season analysis coordination incorporating all 540 games (Months 10–12); event correlation implementation (Months 10–12); manuscript preparation (Months 10–12); and Standard Grant preparation (Months 10–11). 165 hours (average 3.2 hours/week) represents optimal balance, enabling early pipeline validation on initial games, essential oversight during RA appointment for analysing remaining games, and full-season analysis coordination while maintaining other commitments and leveraging PI's established TDA expertise.

Co-Investigators (66 hours total, £5,808)

- Professor Liam Kilduff (33 hours, £2,904): Critical sports science expertise for interpreting topological patterns within professional football context, validating analytical outputs, and translating research findings into practical applications.

- Professor Gibin Powathil (33 hours, £2,904): Essential applied mathematics expertise for TDA methodological guidance, statistical validation, theoretical framework development, and ensuring mathematical rigour for top-tier publications.

33 hours each provides essential domain expertise without duplicating PI efforts, ensuring comprehensive coverage across sports science, applied mathematics, and computational topology.

### Directly Allocated Costs

Estates (£17,828): Justified for dedicated workspace across three departments, access to Supercomputing Wales cluster (2-Petaflops), secure GDPR-compliant data storage (100TB), and facilities for industry partnership meetings and collaboration.
Infrastructure Technicians (£593): Essential technical support for HPC cluster access, data management systems, and open-source library integration.

### Indirect Costs

Indirect Costs (£38,228): Standard institutional overhead covering administrative support, facilities management, IT/library services, and compliance/governance. Calculated at standard rates across three participating departments, reflecting multi-disciplinary nature.

### Infrastructure and Facilities

Institutional Infrastructure (In-Kind): Project leverages existing Supercomputing Wales cluster (2-Petaflops, <1s per-frame processing) enabling concurrent pipeline execution for full-season analysis (~540 games, ~80,000 frame analyses), secure data storage (100TB), institutional software licences, Research Office support, and Impact Officer support at no additional cost, maximising outcomes while minimising direct costs.

### Resource Optimisation Summary

The requested resources represent optimal use to achieve intended outcomes:

- Staff Allocation: PI analyses 15–20 initial games (Months 1–3) + 6-month RA sets up pipeline and analyses remaining games (Months 4–9) + PI coordinates full-season analysis (Months 10–12) + 2 Co-Is (66 hours) ensures comprehensive coverage across computational, theoretical, and domain expertise while maintaining cost-effectiveness for full-season analysis

- Infrastructure Leverage: Utilisation of existing institutional computational and storage infrastructure eliminates need for additional equipment costs

- Open-Source Tools: Primary reliance on mature, free TDA libraries minimises software costs while maximising capability

- Focused Investment: Resources concentrated on essential staff time and directly allocated costs, maximising research quality and impact

- Partnership Value: In-kind data access and expertise from Swansea City AFC provides significant additional value without direct cost

This resource structure ensures all four research objectives are achieved within the 12-month timeline while maximising potential outcomes, impacts, and value for money.

Justification of Resources

Overview and resourcing strategy

This application requests the minimum set of resources required to deliver four tightly scoped objectives over 12 months. The budget prioritises specialist staff time and access to institutional infrastructure to enable full-season analysis of professional football match data using Topological Data Analysis (TDA). The Full Economic Cost is £95,233, with the EPSRC contribution at 80%. Costs are concentrated where they deliver the highest value: a six-month Research Associate (RA) appointment to execute concurrent, large-scale data processing and methods implementation; Principal Investigator (PI) time for scientific leadership, early pipeline validation, and end-to-end coordination; targeted Co-Investigator (Co-I) input for domain expertise and methodological rigour; and access to institutional high-performance computing (HPC), secure storage, and meeting spaces. No new equipment purchases are required; the project leverages mature open-source libraries and existing institutional facilities, ensuring excellent value for money and timely delivery.

Project staff

Research Associate (6 months, 100% FTE).
The RA is essential to achieving all four objectives within the 12-month timeframe. Their primary responsibility is to set up and operate a concurrent processing pipeline and to complete the full-season analysis across the Championship dataset. This entails: (i) implementing persistent homology computations at multiple scales per frame, (ii) undertaking pattern formation method development with temporal tracking and baseline signature identification across at least three tactical systems, (iii) delivering the temporal evolution module using persistence landscapes, and (iv) performing statistical validation, quality control, and comprehensive code documentation.

This allocation is justified on both technical and operational grounds. Preliminary work has established sub-second to two-second per-frame performance on the institutional HPC cluster, making concurrent processing of hundreds of matches tractable. Concentrating specialist effort over months 4–9 allows the RA to (a) complete pipeline setup and optimisation early in their appointment and (b) drive systematic analysis of the remaining matches at scale, while ensuring quality assurance and reproducibility. The RA’s skill set—Python, parallelisation, TDA libraries (ripser, GUDHI, giotto-tda), and statistical analysis—aligns directly with the project’s computational demands and avoids the need for external contractors or additional licences. The appointment length is calibrated to deliver the full season analysis while preserving resource for PI-led integration, write-up, and dissemination in months 10–12.

Principal Investigator (165 hours).
The PI provides scientific direction, methodological leadership, and coordination that cannot be delegated. The PI will: (i) develop and validate the initial pipeline and analyse 15–20 games in months 1–3 to establish a robust foundation; (ii) supervise and mentor the RA during months 4–9, ensuring methodological fidelity and quality standards; (iii) manage the partnership critical for data access (Swansea City AFC–StatsBomb); (iv) coordinate the end-to-end full-season synthesis integrating all 540 matches in months 10–12; and (v) lead event correlation, manuscript preparation, and the subsequent Standard Grant planning. The requested hours (averaging ~3.2 hours/week) represent an optimal balance between strategic oversight, hands-on methodological development, and the PI’s other commitments, ensuring continuity and timely delivery without over-resourcing.

Co-Investigators (66 hours total).
Two Co-Is provide targeted, high-value expertise without duplication of the PI’s role.

- Sports science (33 hours): Interprets topological outputs in the context of professional football tactics, supports validation, and translates findings into practically meaningful insights for performance analysis.

- Applied mathematics (33 hours): Ensures theoretical rigour in TDA methodology, supports statistical validation, and contributes to framework refinement suitable for top-tier publications.

This measured input guarantees comprehensive coverage across computational topology, sports science, and applied mathematics, strengthening the research’s validity and impact while maintaining cost-effectiveness.

Facilities and infrastructure

High-performance computing, secure storage, estates, and technical support are justified as they enable reliable, compliant, and efficient delivery at scale. The project relies on the institutional HPC cluster to execute concurrent pipelines and compute persistent homology across large volumes of match-frame data. Access to secure, GDPR-compliant storage is required to hold raw, intermediate, and processed datasets as well as reproducibility artefacts (code, logs, validation reports). Estates costs provide office and meeting space across the participating departments, facilitating collaboration, supervision, and industry engagement. Modest technician time covers HPC account provisioning, environment setup, data management integration, and support for open-source library dependencies. Crucially, there is no need for new equipment purchases or commercial software licences: the project exploits mature, well-supported open-source TDA libraries, further improving value for money and sustainability.

Optimal use of resources and delivery plan

The resource profile has been carefully phased to maximise productivity and minimise waste:

- Months 1–3: PI develops and validates the pipeline, analyses 15–20 games, and finalises the RA work plan and quality criteria. This early validation de-risks the subsequent scale-up and ensures the RA can begin with a tested framework.

- Months 4–9: RA establishes concurrent processing and completes the full-season analysis across the remaining matches, implements pattern formation and temporal evolution methods, and documents the codebase to reproducible standards. PI supervises, ensuring methodological coherence and timely milestones; Co-Is provide targeted inputs at key decision points (e.g., model assumptions, validation thresholds, interpretation of outputs).

- Months 10–12: PI integrates outputs across all 540 matches, conducts event correlation analyses, finalises figures and tables, and leads manuscript preparation and Standard Grant development.

This plan optimises specialist expertise at the right time, mitigates risks through early validation, and concentrates computationally intensive activity within the RA appointment. It also ensures that dissemination and future funding preparation are resourced appropriately.

Outcomes, impact, and value for money

The requested resources directly support high-impact, reproducible outputs: a validated analytical framework, open and well-documented code, and rigorous multi-match results interpretable by sports scientists and analysts. Leveraging institutional HPC and secure storage eliminates the need for capital expenditure and reduces recurring overheads. Relying on mature open-source libraries removes licensing costs and aligns with EPSRC’s principles on reproducibility and sustainability.

Partnership value is considerable: in-kind full-season data access and domain insight from Swansea City AFC enable a real-world, high-quality dataset without direct cost to EPSRC. This amplifies impact by ensuring that methods and findings are grounded in professional practice, with clear pathways to adoption in performance analysis and coaching contexts. The RA’s involvement in publication and code stewardship supports career development, contributing to the skills pipeline in data-driven sports data-science and computational topology. Collectively, these resources maximise the probability of producing publishable, citable outputs and provide a strong platform for a subsequent Standard Grant.

Risk management and assurance

The phased approach, early pipeline validation by the PI, followed by RA-led scale-up, reduces technical risk and ensures continuity. Institutional facilities guarantee compliance (e.g., data protection) and reliability (e.g., storage redundancy, supported HPC environments). Code documentation, statistical validation, and quality control are embedded throughout, ensuring that results are robust, reproducible, and audit-ready. The modest technician input further mitigates operational risks by providing support where needed without inflating costs.

Closing statement

In summary, the resources requested are comprehensive, appropriate, and justified for the proposed work. They represent optimal use by concentrating investment on specialist staff time and existing institutional infrastructure, avoiding unnecessary equipment or licences. They maximise outcomes and impact by enabling full-season, reproducible analyses grounded in real-world professional football data, with clear pathways to dissemination and future funding. The project is designed to deliver high-quality scientific outputs and practical value within 12 months, providing excellent value for the EPSRC investment.