# VISION AND APPROACH

<!-- JeS Vision & Approach. Restructured 2026-08-21: 7 sections (3 Vision + 4 Approach),

replacing 12-section structure. Merges: §1+§3 → new §1; §2+§4 → new §2; §5+§6 → new §3;

§10+§11+§12 → new §7. Items 2–4 from EPSRC criteria review incorporated.

Strip this comment before JeS submission. -->

## Vision

## 1. Research Problem and Mathematical Contribution

Competitive collective systems are spatially distributed multi-agent systems in a bounded domain, where agents coordinate internally while responding to an active adversary. They arise in autonomous multi-agent coordination, biological collectives and tactical team sports. Statistical topology can already summarise spatial organisation in cooperative collectives, or when observations can be treated as independent. No unified statistical-topological framework yet exists to quantify how large-scale organisation emerges, evolves and undergoes structural transitions under competition. This grant is a proof-of-principle for that framework: it proves the foundational theorems and builds the full-season evidence base that a follow-on Standard Grant will transfer across domains.

**Importance.** Two obstacles limit existing approaches. Organisational structure exists at several spatial scales at once: small interaction groups, larger formations and enclosed coverage regions coexist, yet single-threshold persistent homology [1–3] folds their signatures into one picture and hides scale-specific structure. Observations are also strongly dependent: each agent continuously adapts to its opponents, violating the exchangeability assumptions that underpin current statistical topology [6,8]. Multiparameter persistence [4,5] offers a theoretical route but remains computationally intractable at competitive data rates.

**Mathematical contribution.** Two theorem-level results are targeted. (T1) A unique mean path of landscape-valued topological summaries exists when observations are dependent and competitive, not only when they are exchangeable [6]. The landscape representation's linear structure secures uniqueness; boundedness of the domain discharges the integrability condition. (T2) Detected transitions can be localised with a proven error bound: a Wasserstein-stability result for a sequential change-point (CUSUM) statistic on landscape-valued series, under temporal dependence and a bounded domain. T1 and T2 are proved and tested through two research objectives: O1 establishes the population-scale geometry on which T1 rests; O2 delivers the proofs and validates T2 at season scale (§4).

**Quality.** T1 and T2 are stated as explicit, checkable claims — the results are proved or they are not. Interaction lengths are set by stability-validated spatial scales already recovered at pilot scale [17] and re-derived if they fail to transfer. Professional football tracking data provide a fully observed, spatially bounded, population-scale testbed on which both theorems are calibrated and tested.

## 2. Background, Timeliness, Need and Opportunity

Topological methods have shown that spatial organisation in multi-agent systems carries structure, demonstrated in biological aggregation, collective motion and flocking [11–13] and topological change-point detection [14]. These applications rely on persistent homology [1,2]and its statistical summaries [6,8,9] to track qualitative shape features across scales —summaries stable under small measurement error [7], enabling formal comparison and averaging. Multi-scale methods exist for cooperative, slowly evolving systems [10], but not for hierarchical competitive dynamics. Conventional approaches remain single-scale geometric descriptors [15,16]. Our pilot [17] takes a first step, recovering three stable connected-component regimes and two complementary loop regimes across 10 realisations of a competitive collective system, in which the scales carry largely independent information.

**Timeliness.** Three developments have converged: multi-scale topology and statistical comparison tools have reached maturity [4,6,8,9,11–14]; scalable computation now supports rigorous analysis of high-frequency interaction data at population scale (§5); and fully labelled competitive tracking data have become available at the same scale. No statistical-topology treatment of competitive collective systems yet combines these three.

**Need and opportunity.** The mathematical gap is specific: no validated statistical-topology workflow exists for systems generated by continuous competitive interaction, because existing inference methods provide theoretical guarantees only in static, single-scale or exchangeable settings. Professional football provides the opportunity to close it — a well-observed platform where all agents are continuously tracked within strict spatial boundaries and domain experts can verify results. The resulting framework generalises to any bounded competitive system once interaction lengths are re-derived.

## 3. Impact and Beneficiaries

**Mathematical impact.** The primary contribution is new statistical-topology theory for dependent competitive systems: the mean-path (T1) and Wasserstein-stability (T2) results extend current foundations [6,8] to sequential adversarial dynamics. Both are implemented in an open-source library for competitive point-cloud analysis, and the primary beneficiaries — researchers in topology, statistics and complex systems — gain new theoretical foundations for inference on dependent spatial data and the software to apply them. **National importance.** UK groups lead internationally in statistical topology [6,8] and stochastic geometry, but current methods remain confined to static or exchangeable settings. This project develops UK capability at the frontier of statistical TDA, spatial point processes and sequential inference on abstract

metric spaces, aligning with EPSRC priorities in mathematical sciences, AI-enabled modelling and complex systems. **Economic and industry impact.** The project is co-developed with Swansea City AFC (SCAFC), delivering practitioner outputs unavailable from conventional geometric measures; secondary beneficiaries are sports analytics researchers and practitioners who receive interpretable structural measures of collective organisation. **Standard Grant pathway.** The T1/T2 foundations proved here prepare a follow-on Standard Grant transferring the guarantees to spatial predator–prey dynamics, including tumour–immune competition with Co-I Powathil; broader competitive-domain beneficiaries will be addressed in that programme.

## Approach

## 4. Research Design and Objectives

**Project structure.** The PI (0.2 FTE) leads framework development, analysis and publication. Two Co-Investigators (0.1 FTE combined) supply statistical and domain expertise. A Research Associate (Months 2–10) implements the computational pipeline and conducts the full-season analysis, developing cross-disciplinary competence in statistical topology, sequential inference and applied sport science — a combination that constitutes structured postdoctoral training in competitive-systems methodology. SCAFC provides tracking data and tactical labels.

**Sample-size rationale.** A Championship season (≈540 matches) supplies the replication the 10 realisation pilot cannot. Approximately 32 matches per covariate subgroup (phase of play, opponent strength or venue) yield a 95% CI half-width of 0.025 for the match-level tactical-scale loop-presence rate (pilot across-match s.d. 0.072 [17]). Separately, 180 matches per tactical formation detect Cohen's d ≥ 0.30 at 80% power (α=0.05, Benjamini–Hochberg FDR). A borderline within-match pilot effect (p=0.051) is the replication target.

**O1: Population-scale geometry (PI Months 1–9; RA Months 2–9).** O1 determines whether scale-specific topological summaries are stable enough to average at population scale, and whether distances between those summaries distinguish competitive organisational states beyond conventional geometric descriptors [6,8], using a 20-match validation batch to test cutoff transferability. Success criteria: cutoff stability ≥ 0.80 (below this, interaction lengths are re-derived); moment conditions documented at season scale; discriminable signatures for ≥3 tactical formations (FDR-corrected differences, p<0.05). Milestones: OSF pre-registration of hypotheses and exclusion rules, Month 2; cutoff gate, Month 2; barcode database and moment conditions, Month 7; comparison-geometry results, Month 9.

**O2: Inference for dependent topological processes (PI and RA, Months 4–10).** O2 proves the §1 theorems using functional principal component analysis (FPCA) [18], CUSUM [19] and bootstrap calibration [6]. Success criterion: change-points agree with held-out annotations at ≥70% (permutation p < 0.05); fallback is direct Wasserstein diagram comparison, already demonstrated in the pilot. Milestones: landscape module Month 8; T1/T2 statements and calibrated change-point outputs, Month 9; results finalised for the season paper, Month 10.

## 5. Methodology

A containerised Python pipeline processes each match frame as a point cloud. Agents are partitioned using empirically derived interaction lengths validated against a three-scale stability criterion: H₀ and H₁ barcode profiles must reproduce the pilot's three connected-component and two loop regimes within tolerance across a 20-match validation batch; scales that fail are re-derived before production processing begins. Persistent homology is computed at each accepted scale using Ripser [20], GUDHI [21] and giotto-tda [22], producing barcodes converted to persistence landscapes for the O2 time-series analysis and to diagram-image features [9] for the O1 classification task. Production processing runs at 1 Hz on Supercomputing Wales (§7).

For O1, landscape distributions are compared across tactical formations and covariate subgroups using persistence-based distances, with discriminability tested by permutation tests under BH-FDR correction. Hypotheses and exclusion criteria are pre-registered on OSF (Month 2) to prevent post-hoc selection. For O2, landscape-valued time series are summarised using FPCA [18], reducing each topological trajectory to a low-dimensional functional representation while retaining within-landscape

structure that scalar features discard. CUSUM statistics [19] are applied to the FPCA scores with detection thresholds calibrated by block bootstrap, using the pilot's inter-match dependence structure as the resampling block length. T1 is established by verifying that the coordinate-wise landscape mean is stable under the seasonal dependent data distribution; T2 is validated by comparing detected change-points against held-out event annotations. Reproducibility is ensured throughout via containerisation, version-controlled code, OSF pre-registration and DOI-archived software releases.

## 6. Feasibility and Risk Management

The project is feasible in twelve months because the method is pilot-validated (§2), data access is secured through the SCAFC agreement, and the computational budget is modest relative to the available allocation (§7). The pilot has already fixed the parameter ranges over which T1 and T2 are stated, so O2 begins from established conditions rather than from scoping work. Three residual risks remain. (R1) Scale transferability (medium likelihood, high impact): without transferable interaction lengths, averaging is not meaningful; the Month-2 cutoff gate re-derives them if stability falls below 0.80. (R2) Tactical label uncertainty (medium likelihood, low impact): dual-source verification, Cohen's κ and pre-registered exclusions mitigate this; labels affect O1 interpretation, not the theorems. (R3) Landscape theory (low likelihood, medium impact): if the landscape argument is intractable, O2 uses the Wasserstein diagram comparison already demonstrated in the pilot, and T1 uniqueness is not claimed.

## 7. Outcomes, Team and Resources

**Publications and software.** The methodology paper [17] is submitted in Months 1–2; a full-season results paper at Month 11; and the companion football-analytics paper [23] at Month 12. The open-source library is released as a documented package with DOI via Swansea University's Zenodo community, forming the principal reproducibility artefact for both papers. Practitioner outputs with SCAFC (Month 11) let analysts review how collective organisation changes around important match events, going beyond conventional geometric descriptors (length, width, centroid) [15,16]. Library, publications and practitioner outputs together form the Month-12 evidence pack for the follow-on Standard Grant (§3).

**Team.** The project is based at Swansea University's Zienkiewicz Institute for Modelling, Data and AI (ZI) and brings together expertise not previously combined in a single grant: statistical topology (PI), mathematical oncology (Co-I Powathil) and sport and exercise science (Co-I Kilduff), with SCAFC as the live industry co-development setting. This new interdisciplinary collaboration bridges communities with distinct analytical traditions — mathematical, biological and sporting — through a shared topological framework, making it a natural fit for the Small Grant scheme's new-collaboration remit. Prof Kilduff supplies the sport-science judgement that turns organisational-state distinctions into tactically meaningful categories, grounding the practitioner outputs; Prof Powathil positions the T1/T2 results for the health-science pathway the Standard Grant will pursue.

**Resources.** Full-season processing uses the PI's Supercomputing Wales allocation: approximately 1,600 CPU-hours of a 5,000 CPU-hour available budget. The containerised pipeline is executable on local machines and high-performance computing clusters. Swansea University provides host and research support through ZI and the University Research Office, with data-governance and ethics processes established for the SCAFC data.

## References

1. Carlsson, G. (2009). Topology and data. *Bulletin of the American Mathematical Society*,

46(2), 255–308.

2. Zomorodian, A. & Carlsson, G. (2005). Computing persistent homology. *Discrete &

Computational Geometry*, 33(2), 249–274.

3. Edelsbrunner, H. & Harer, J. (2010). *Computational Topology: An Introduction*. American

Mathematical Society.

4. Botnan, M. B. & Lesnick, M. (2022). An introduction to multiparameter persistence. In

*Representations of Algebras and Related Structures* (pp. 77–150). EMS Press.

5. Lesnick, M. (2015). The theory of the interleaving distance on multidimensional persistence

modules. *Foundations of Computational Mathematics*, 15(3), 613–650.

6. Chazal, F., Fasy, B. T., Lecci, F., Rinaldo, A. & Wasserman, L. (2014). Stochastic

convergence of persistence landscapes and silhouettes. *Proceedings of the 30th Annual

Symposium on Computational Geometry*, 474–483.

7. Cohen-Steiner, D., Edelsbrunner, H. & Harer, J. (2007). Stability of persistence diagrams.

*Discrete & Computational Geometry*, 37(1), 103–120.

8. Bubenik, P. (2015). Statistical topological data analysis using persistence landscapes.

*Journal of Machine Learning Research*, 16(1), 77–102.

9. Adams, H. et al. (2017). Persistence images: a stable vector representation of persistent

homology. *Journal of Machine Learning Research*, 18(8), 1–35.

10. Schindler, D. J. & Barahona, M. (2023). Analysing multiscale clusterings with persistent

homology. arXiv:2305.04281.

11. Topaz, C. M., Ziegelmeier, L. & Halverson, T. (2015). Topological data analysis of

biological aggregation models. *PLoS ONE*, 10(5), e0126383.

12. Bhaskar, D. et al. (2019). Analysing collective motion with machine learning and topology.

*Chaos*, 29(12), 123125.

13. Ballerini, M. et al. (2008). Interaction ruling animal collective behaviour depends on

topological rather than metric distance. *PNAS*, 105(4), 1232–1237.

14. Gu, K. et al. (2022). Change point detection in multi-agent systems based on higher-order

features. *Chaos*, 32(11), 113117.

15. Folgado, H. et al. (2014). Length, width and centroid distance as measures of teams'

tactical performance in youth football. *European Journal of Sport Science*, 14(S1),

S487–S492.

16. Fernández, J. & Bornn, L. (2018). Wide open spaces: a statistical technique for measuring

space creation in professional soccer. *Sloan Sports Analytics Conference*.

17. Brown, R. et al. (2026). Multi-scale persistent homology for competitive spatial systems:

measurement-aware methods and validation in professional football. ArXiv preprint; submitted

to the *Journal of Applied and Computational Topology*.

18. Ramsay, J. O. & Silverman, B. W. (2005). *Functional Data Analysis* (2nd ed.). Springer.

19. Page, E. S. (1954). Continuous inspection schemes. *Biometrika*, 41(1/2), 100–115.

20. Bauer, U. (2021). Ripser: efficient computation of Vietoris–Rips persistence barcodes.

*Journal of Applied and Computational Topology*, 5(3), 391–423.

21. Maria, C., Boissonnat, J.-D., Glisse, M. & Yvinec, M. (2014). The Gudhi library:

simplicial complexes and persistent homology. In *Mathematical Software – ICMS 2014*

(pp. 167–174). Springer.

22. Tauzin, G. et al. (2021). giotto-tda: a topological data analysis toolkit for machine

learning and data exploration. *Journal of Machine Learning Research*, 22(39), 1–6.

23. Brown, R. et al. (2026). Multi-scale topological signatures of tactical organisation in

professional football. In preparation; to be submitted to the *Journal of Sports Sciences*.